## Sheet1
Task | Start Date | End Date | Duration
WP0.0: Individual SWOT | 2021-01-06 | 2021-01-07 | 1
WP0.1: Team Formation | 2021-01-06 | 2021-01-07 | 1
WP0.2: Team SWOT | 2021-01-20 | 2021-01-23 | 3
WP0.3: PID | 2021-01-20 | 2021-01-23 | 3
WP0.4: PMP | 2021-01-26 | 2021-01-30 | 4
WP1.1: Research LED Lights | 2021-01-29 | 2021-02-01 | 3
WP1.2: Discuss LED Lights | 2021-02-01 | 2021-02-02 | 1
WP1.3: Buy LED Lights | 2021-02-02 | 2021-02-03 | 1
WP1.4: Receive LED Lights | 2021-02-03 | 2021-02-17 | 14
WP1.5: Integrate LEDs with Arduino | 2021-02-17 | 2021-02-19 | 2
WP1.6: Research Motors | 2021-01-30 | 2021-02-01 | 3
WP1.7: Discuss Motors | 2021-01-30 | 2021-02-02 | 1
WP1.8: Buy Motor | 2021-02-02 | 2021-02-03 | 1
WP1.9: Receive Motor | 2021-02-03 | 2021-02-17 | 14
WP1.10: Integrate Motor with Arduino | 2021-02-17 | 2021-02-19 | 2
WP1.11: Begin researching remaining sensors | 2021-01-29 | 2021-02-01 | 3
WP1.12: Research GUI in MATLAB | 2021-01-29 | 2021-02-01 | 3
WP1.13: Demo for Milestone 1 | 2021-02-22 | 2021-02-22 | 0
WP1.14: Postmortem and Peer Review 1 | 2021-02-22 | 2021-02-27 | 5
WP2.1: Research Temperature Sensor and Heater | 2021-01-29 | 2021-02-01 | 3
WP2.2: Discuss Temperature Sensor and Heater | 2021-02-01 | 2021-02-02 | 1
WP2.3: Buy Temperature Sensor | 2021-02-02 | 2021-02-03 | 1
WP2.4 Recieve Temperature Sensor | 2021-02-03 | 2021-02-17 | 14
WP2.5: Integrate Temperature Sensor and Heater with Arduino | 2021-03-03 | 2021-03-05 | 2
WP2.6: Research methods of waterproofing electronic components | 2021-01-29 | 2021-02-01 | 3
WP2.7: Discuss methods of waterproofing | 2021-02-01 | 2021-02-02 | 1
WP2.8: Buy method of waterproofing | 2021-02-02 | 2021-02-03 | 1
WP2.9: Receive method of waterproofing | 2021-02-03 | 2021-02-17 | 14
WP2.10: Implement waterproofing | 2021-03-03 | 2021-03-05 | 2
WP2.11: Research data displaying in MATLAB | 2021-01-29 | 2021-02-01 | 3
WP2.12: Discuss data displaying in MATLAB | 2021-03-03 | 2021-03-04 | 1
WP2.13: Implement data display in MATLAB with current components | 2021-03-04 | 2021-03-06 | 2
WP2.14: Incorporating elements with GUI | 2021-03-06 | 2021-03-08 | 2
WP2.15: Demo for Milestone 2 | 2021-03-22 | 2021-03-22 | 0
WP2.16: Milestone 2 Postmortem and Peer Review | 2021-03-22 | 2021-03-27 | 5
WP3.1: Research pH sensors | 2021-01-29 | 2021-02-01 | 3
WP3.2: Discuss pH sensors | 2021-02-01 | 2021-02-02 | 1
WP3.3: Buy pH sensor | 2021-02-02 | 2021-02-03 | 1
WP3.4: Receive pH Sensor | 2021-02-03 | 2021-02-17 | 14
WP3.5: Implement pH Sensor with Arduino | 2021-03-31 | 2021-04-02 | 2
WP3.6: Incorporate pH and final details into GUI | 2021-04-02 | 2021-04-04 | 2
WP3.7: Testing final system/doing quality checks | 2021-04-05 | 2021-04-08 | 3
WP3.8: Finalize data displaying methods in MATLAB | 2021-04-05 | 2021-04-08 | 3
WP3.9: Video of Final System | 2021-04-18 | 2021-04-21 | 3
WP3.10: Demo of Final Project | 2021-04-12 | 2021-04-12 | 0
WP3.11: Final Report | 2021-04-17 | 2021-04-22 | 5
WP3.12: Final Postmortem and Peer Review | 2021-04-17 | 2021-04-22 | 5
Formulas:
End Date = [Start Date]+1
End Date = [Start Date]+[Duration]
Start Date = [End Date]-[Duration]
Start Date = [End Date]-[Duration, row above]

## Sheet2
Task | Skills | Equipment | Materials
WP0.0: Individual SWOT
WP0.1: Team Formation |  |  | Individual SWOT
WP0.2: Team SWOT |  |  | Individual SWOT
WP0.3: PID
WP0.4: PMP |  |  | PID
WP1.1: Research LED Lights | Knowledge of what works with Arduino | Computer
WP1.2: Discuss LED Lights |  | Computer
WP1.3: Buy LED Lights |  | Computer
WP1.4: Receive LED Lights
WP1.5: Integrate LEDs with Arduino | How the LEDs/other compnents work | Arduino, Computer with MATLAB | LEDs, MOSFETs, resistors, wires
WP1.6: Research Motors | Knowledge of what works with Arduino | Computer
WP1.7: Discuss Motors |  | Computer
WP1.8: Buy Motor |  | Computer
WP1.9: Receive Motor
WP1.10: Integrate Motor with Arduino | How the motor, MATLAB and 3D printer work | Arduino, Computer with MATLAB | Motor, 3D Printer, wires
WP1.11: Begin researching remaining sensors | Knowledge of what works with Arduino | Computer
WP1.12: Research GUI in MATLAB |  | Computer
WP1.13: Demo for Milestone 1 |  | System/Computer with MATLAB
WP1.14: Postmortem and Peer Review 1 | Knowledge of how Milestone 1 went | Computer
WP2.1: Research Temperature Sensor and Heater | Knowledge of what works with Arduino | Computer
WP2.2: Discuss Temperature Sensor and Heater |  | Computer
WP2.3: Buy Temperature Sensor |  | Computer
WP2.4 Recieve Temperature Sensor
WP2.5: Integrate Temperature Sensor and Heater with Arduino | How the temperature sensor and heater works | Arduino, Computer with MATLAB | Temperature sensor, wires
WP2.6: Research methods of waterproofing electronic components | Basic Knowledge of Waterproofing | Computer
WP2.7: Discuss methods of waterproofing |  | Computer
WP2.8: Buy method of waterproofing |  | Computer
WP2.9: Receive method of waterproofing
WP2.10: Implement waterproofing |  | heat shrink tubing/acrylic sheet | Components for system
WP2.11: Research data displaying in MATLAB |  | Computer
WP2.12: Discuss data displaying in MATLAB |  | Computer
WP2.13: Implement data display in MATLAB with current components | Knowledge of how charts work | Computer, MATLAB
WP2.14: Incorporating elements with GUI |  | Computer, MATLAB
WP2.15: Demo for Milestone 2 |  | System/Computer with MATLAB
WP2.16: Milestone 2 Postmortem and Peer Review | Knowledge of how Milestone 2 went | Computer
WP3.1: Research pH sensors | Knowledge of what works with Arduino | Computer
WP3.2: Discuss pH sensors |  | Computer
WP3.3: Buy pH sensor |  | Computer
WP3.4: Receive pH Sensor
WP3.5: Implement pH Sensor with Arduino | How the pH sensor works | Arduino, Computer with MATLAB | pH sensor, wires
WP3.6: Incorporate pH and final details into GUI |  | Computer with MATLAB
WP3.7: Testing final system/doing quality checks |  | System/Computer with MATLAB
WP3.8: Finalize data displaying methods in MATLAB |  | System/Computer with MATLAB
WP3.9: Video of Final System |  | Camera
WP3.10: Demo of Final Project |  | System/Computer with MATLAB
WP3.11: Final Report | Knowledge of how the system. Works | Computer
WP3.12: Final Postmortem and Peer Review | Knowledge of how the Final system went | Computer